## Modifications (hidden)
Item No. | Description | Unit | Qty | SOLECO Rate (USD) | Amount USD | Evaluated Rate(Ugx) by T&T | Amount (Ugx) | Amount | Comments
ARCHITECTURAL
1 | MODIFICATION 1
150mm thick internal divisions blockwalls to be changed to 100mm thick
Solid Blockwork; Compressive strength 7N/mm2 in cement
sand (1:3) mortar : with and including hoop iron wall ties
OMIT
1.1 | 150mm thick block walls | m2 | -520 | 23.83 | -12391.6 |  |  | -43781400
ADD
1.2 | 100mm thick block walls | m2 | 520 | 19.83 | 10311.6 |  |  | 37112400
| Sub Total(cost implication) |  |  |  | -2080
3 | MODIFICATION 2
3 | Change the outer walls along the cashier to offices from block walls to reinforced concrete walls
OMIT
Solid Blockwork; Compressive strength 7N/mm2 in cement
sand (1:3) mortar : with and including hoop iron wall ties
every alternate course/reinforcement
3.1 | 150mm thick block walls | m2 | -36 | 23.83 | -857.88
ADD
VIBRATED REINFORCED CONCRETE CLASS 25
(20MM AGGREGATE) IN:
3.2 | 200mm thick RC walls | M2 | 36 | 25.74 | 926.64 |  | 0
ROUGH FORMWORK
3.3 | To RC Walls | m2 | 72 | 9 | 648
REINFORCEMENT
3.4 | Reinforcement at 180kg/m3,this to be confirmed with BBS | kg | 1440 | 1.36 | 1958.4
| Sub total (Cost Implication) |  |  | USD | 2675.16
MODIFICATION 3
Addition of two mild steel roller shutter doors infront of the high speed doors in the dispatch area
4 | Manual chain operated and Motorised steel slatted roller shutter door : as supplied by an approved manufacturer including brackets, bolts, etc for fixing against wall finish : complete with steel rolling gear and housing : aluminium painted finish, as per the architects detailed drawing
4.1 | Door, overall size 2000x4000mm high to Architect's detailed drawing(Rate only) | no. | 2 | 1181.9444 | 2363.8889 | 4255000 | 8510000 |  | Considered reasonable
| Sub total (Cost Implication) |  |  | USD | 2363.8889
MODIFICATION 4
The two motorised roller shutter doors,ODO7 and ODO8 in the dispatch area, are not insulated
Motorized insulated sectional Doors with powder
coated aluminium insulated shutter,weighted sound
reduction door curtain with insulation to mechanical
engineer's specs.safety features that comply with BS
EN 12453 and BS EN 12604,electrical controls and
accessories to electrical engineer's specs. as per
architect's detailed drawings
OMIT
5.1 | Door,overall size 3000x4000mm High,Type 0D07 and 0D08 as per the architect's drawing No.c31-02 | no. | -2 | 6795 | -13590 |  | 0
Non Insulated Motorized sectional Doors with powder
coated aluminium insulated shutter,weighted sound
reduction door curtain with insulation to mechanical
engineer's specs.safety features that comply with BS
EN 12453 and BS EN 12604,electrical controls and
accessories to electrical engineer's specs. as per
architect's detailed drawings
ADD
5.2 | Door,overall size 3000x4000mm High,Type 0D07 and 0D08 as per the architect's drawing No.c31-02 | no. | 2 | 5071.9792 | 10143.9583 | 18259125 | 36518250 |  | Considered reasonable
| Sub total (Cost Implication) |  |  |  | -3446.0417
6 | MODIFICATION 5
Extension of the boundary wall by 4m at both sides at the future expansion area
(ALL PROVISIONAL)
EARTHWORKS
EXCAVATION, FILLING, ETC OTHER THAN BULK
Excavation in earth not exceeding 2m deep
6.1 | Trenches | m3 | 8.28 | 3.6 | 29.808
Extra over all excavations for carting away
6.2 | Surplus material from excavations and/or stock piles on site to | m3 | 6 | 4.5 | 27
a dumping site to be located by the Contractor
FILLING ETC
Earth filling obtained from the excavations and/or
prescribed stock piles on site in 150mm layers compacted
to 95% Mod AASHTO density
6.3 | Backfilling to trenches, holes, etc | m3 | 4 | 3.6 | 14.4
SOIL POISONING
Soil insecticide
6.4 | To bottoms and sides of trenches, holes, etc | m2 | 29.52 | 0.9 | 26.568
CONCRETE, FORMWORK AND
REINFORCEMENT
CONCRETE WORK
PLAIN CONCRETE CLASS 15 (20MM AGGREGATE)
6.5 | 50mm under strip footings | m2 | 5.52 | 5.65 | 31.188
VIBRATED REINFORCED CONCRETE CLASS 25
(20MM AGGREGATE) IN:
FOUNDATIONS AND SUBSTRUCTURE
6.6 | Strip footings | m3 | 1.104 | 128.7 | 142.0848
REINFORCEMENT
Mild steel reinforcement to structural concrete work (BS
4449)
6.7 | Reinforcements at 180kg/m3, to be confirmed with BBS | Kg | 198 | 1.36 | 269.28
HONEY COMBING RETAINING WALL
PRECAST CONCRETE CLASS 20, finished fair on all
exposed surfaces including bedding and jointing in
cement sand (1:3) mortar
6.8 | Concrete block honey combs | m2 | 8 | 41.38 | 331.04
BLOCK WORK
Block walling; Compressive strength 7 N/mm2
OMIT
6.9 | 200mm Thick boundary wall | m2 | -835 | 24.63 | -20566.05
ADD
| ENGINEERING BRICKS; jointed and pointed in cement sand (1:3) mortar : with and including hoop iron wall ties every alternate course built into concrete columns : in |  |  |  | 0
| 230mm thick brick wall finished to schedule | m2 | 859 | 39.5 | 33930.5 | 90000 | 77310000 |  | Please review this rate and provide breakdown
COPING
0
6.1 | Provide for 200mm thick clay tiles coping as per the architects | Lm | 8 | 3 | 24
detailed drawing No A(91) 01-03
DRAINAGE
6.2 | Approved 20mm aggregate granular fill, well compacted as per | m3 | 0.96 | 47.5 | 45.6
Structural Engineers detailed drawing
6.3 | 150mm Diameter porous or open jointed concrete pipe laid to | Lm | 8 | 11.25 | 90
fall 1:200 in 20mm aggregate surround as per Structural
Engineers detailed drawing
| Sub total (Cost Implication) |  |  |  | 14395.4188
MODIFICATION 6
Gravel to be placed underneath the storage containers to minimise moisture and
water which may damage the containers
7.1 | Excavate average 200mm deep commencing at reduced level | m3 | 49.8 | 3.6 | 179.28
but not exceeding 2m deep; deposit in temporary spoil heaps
on site
7.2 | Approved imported murram fill: well compacted in layers not | m3 | 74.7 | 10.8 | 806.76
exceeding 150mm thick using 15 ton vibrating roller to 95%
MDD ASHTO to Engineer's approval.
7.3 | Compact existing sub grade to 93% MDD, (MOD AASHTO), | m2 | 249 | 1.25 | 311.25
CBR>15%
7.4 | 200mm bed of gravel on compacted ground. | m2 | 249 | 3.24 | 806.76
| Sub total (Cost Implication) |  |  |  | 2104.05
MODIFICATION 7
8 | Addition of landscaping in the area after the extension of the boundary wall and in the road reserves
8.1 | Dig out to break existing ground and all weeds and roots, supply, spread and level 300mm red imported soil and mix with manure and general fertilizer including planting approved grass tufts at 100mm centres in each direction including watering until established. | Sm | 1000 | 5.5556 | 5555.5556 | 18000 | 18000000 |  | Please review this rate
| Sub total (Cost Implication) |  |  |  | 5555.5556
STRUCTURAL
MODIFICATION 9
9 | Change from painted finished mild steel to hot dipped galvanised steel
SPIRAL STAIRCASE
| Galvanised structural steelwork for the spiral staircase includes; all plates, bolts, haunchings, cleats, welded joints and all connections as per the architect's detailed drawings L(44) 07-09 |  |  |  | 66.44
9.1 | 100mm diameter,3mm thick CHS centre pole. | kg | 44 | 1.51 | 2088.74 |  | 0 | 239492
9.2 | 4mm thick galvanised steel checker plate tread with abrasive coating for the spiral staircase | kg | 1154 | 1.81 |  |  | 0 | 7498692
ROOF RAFTERS, TIE BEAMS AND TIES AND STRUTS
The rate fo structural steelwork should include all plates, bolts, welded joints and all connections as per Engineer's detailed drawings
| Note: All hot rolled steel sections, plates and flats shall be to grade S275 to BS EN 10025. Hollow sections shall be to S355J0H to BS EN 10210 as per the engineer's detailed specifications and drawing |  |  |  | 8072.46
9.3 | 305x102x33kg/m UB,beams | kg | 5346 | 1.51 | 229.52 |  | 0 | 29098278
9.4 | 60x40x3mm SHS truss 01 | kg | 152 | 1.51 | 2009.81 |  | 0 | 827336
9.5 | 80x40x3mm SHS truss 02 | kg | 1331 | 1.51 | 4919.58 |  | 0 | 7244633
9.6 | 150x100x3mm RHS | kg | 3258 | 1.51 | 7080 |  | 0 | 17733294
9.7 | 16mm threaded rods supports for the lights and AC cassettes in the picking area | kg | 3540 | 2 | 7507.72
9.7 | 100x100x3mm SHS | kg | 4972 | 1.51 | 767.08
9.8 | 40X40X3mm SHS | kg | 508 | 1.51 | 3125.7 |  | 0 | 2765044
9.9 | IPE 160 Steel beam fixed on rafters | kg | 2070 | 1.51 | 4878.81 |  | 0 | 11267010
9.1 | 100X50X3mm RHS steel beams fixed on truss | kg | 3231 | 1.51 | 819.93
9.11 | 30X30X3mm SHS | kg | 543 | 1.51 | 206.87
9.12 | 115X50X2mm purlins | kg | 137 | 1.51 | 8191.75
9.13 | 254x146x31kg/m vertical supports to wall cladding | kg | 5425 | 1.51 | 5662.5
9.14 | 610x229x125kg/mUB,columns. | kg | 3750 | 1.51 | 1315.21
9.15 | 533X210X101kg/mUB,columns | kg | 871 | 1.51 | 3687.42
9.16 | 50x50x6mm RSA Eaves gutter stub rafter | kg | 2442 | 1.51 | 6100.4
9.17 | 406X178X54kg/mUB,columns | kg | 4040 | 1.51 | 317.1
9.18 | 80x40x3RHS supports to the smoke vents | kg | 210 | 1.51 | 533.03
9.19 | 12mm sag rods | kg | 353 | 1.51
PURLINS, BRACING, ETC
| Purlins welded to steel |  |  |  | 5889
9.2 | 75x75x6 RSA wind bracing | kg | 3900 | 1.51 | 13843.68 |  | 0 | 21227700
9.21 | 150x50x20x2.5Zed purlins | kg | 9168 | 1.51 |  |  | 0 | 49901424
| Haunches |  |  | 1.51 | 5946.38
9.22 | 3150 x 450 Haunching cut from 610 x 229 x 125Kg/m welded to portal frame | kg | 3938 | 1.51 | 942.24 |  | 0 | 21434534
9.23 | 3100 x 450 Apex haunching cut from 406 x 140 x 39 Kg/m welded to portal frame | kg | 624 | 1.51 |  |  | 0 | 3396432
Sundries
Descriptions of bolts shall be deemed to include nuts and washers
Descriptions of Holding Down bolts shall be deemed to includebending, threading, nuts and washers and embedding in concrete
| Descriptions of expansion anchors and bolts and chemical anchors and bolts shall be deemed to include nuts, washers and mortices in brickwork or concrete |  |  |  | 431.35
9.24 | 743 x 359 x 20mm Base plates including non shrink grout | No | 5 | 86.27 | 168.6 |  | 0 | 1552865
9.25 | 382 x 277 x 18mm Base plates including non shrink grout | No | 5 | 33.72 | 871.56 |  | 0 | 607135
9.26 | 220x 130 x 8mm Thick horizontal cleats | No | 269 | 3.24 | 356.4 |  | 0 | 3146493
9.27 | 220 x 130 x 8mm Thick horizontal fish plates | No | 110 | 3.24 | 664.2 |  | 0 | 1286670
9.28 | 220x 130 x 8mm Thick vertical cleats | No | 205 | 3.24 | 94.14 |  | 0 | 2397885
9.29 | 260x180x8mm thick connection plates | No | 18 | 5.23 | 874.25 |  | 0 | 339192
9.3 | 220x 130x 8mm Thick vertical fish plates | No | 269 | 3.25 | 4732.5 |  | 0 | 3146493
9.31 | 1160 x 600 x 16mm Thick connection plate | No | 30 | 157.75 | 996.36 |  | 0 | 17037750
9.32 | 320 x 150 x 16mm Thick mild steel plates at bracing connection to trusses | No | 92 | 10.83 |  |  | 0 | 3586896
| Anchor bolts |  |  |  | 106.4
9.33 | 22mm Diameter HD bolts 900mm long cast into concrete; head, nut and washers; Structural Engineer's detail | No | 20 | 5.32 | 214 |  | 0 | 383300
9.34 | 16mm Diameter HD bolts U-shaped 950mm long cast into concrete; head, nut and washers; Structural Engineer's detail | No | 20 | 10.7 | 49.5 |  | 0 | 770400
9.35 | 16mm diameter Galvanised H.T.bolts | No | 150 | 0.33 | 147.82 |  | 0 | 175500
9.36 | 12mm diameter bolts | No | 778 | 0.19 |  |  | 0 | 525150
| Cat ladder |  |  |  | 375
9.37 | 4m long cat ladder consisting of 50x6mm galvanised mild steel flat to form stringers welded to 50x6mm fishtailed galvanised mild steel and fixed to wall,with 15mm dia.galvanised mild steel rungs welded to 50x6mm mild steel stringers at 300mm centres.,50x6mm thick fishtailed galvanised mild steel flat welded to stringer and cast into wall at 305-345 spacing,50x6mm with 50x6mm galvanised.mild steel flat to form spacer built into wall and welded to stringer at 600mm centres as per the architect's drawing No.A(44)09 | Item | 1 | 375 |  |  |  | 1350000
MODIFICATION 8
9 | The AC cassettes and Lights supports to be changed from 50x50x3mm SHS to
high tensile cables/wires
OMIT
9.1 | 50x50x3mm SHS | Kg | -3540 | 1.51 | -5345.4
ADD
9.2 | 16mm threaded rods supports for the lights and AC cassettes in the picking area,including all connections and accessories | Kg | 3540 | 6.65 | 23541 | 10800 | 38232000 |  | Please review this rate and provide breakdown and supplier
| Sub total (Cost Implication) |  |  |  | 18195.6
MODIFICATION 9
10 | Change from painted finished mild steel to hot dipped galvanised steel
ON METAL
One coat acrylic emulsion metal primer, one coat universal
undercoat and two coats high gloss enamel paint
OMIT
10.1 | On structural steel; Generally | Kg | -57331 | 0.26 | -14906.06
ADD
83700
10.2 | Change from painted finish to Hot Dipped on structural Steel | kg | 62000 | 1.35 | 83700 | 4680 | 290160000 |  | Please review this rate
| Sub total (Cost Implication) |  |  |  | 68793.94
11.2 | The Warehouse AC to be removed out of the scope of the main contractor | Sum |  |  | -105154.71
MECHANICAL AND ELECTRICAL MODIFICATIONS
POWER FACTOR CORRECTION BANK
A | 100kVAR 6-Steps Self-contained, automatic and manual-control self-protecting Power Factor Correction capacitor bank c/w separate low-voltage 250A power circuit breaker to connect the APFC equipment to the switchgear with cable connection, three-phase circuit breaker-protected, contactor-controlled, transient suppressors, discharge resistors, and all the neccessary instrumentation, fixing and wiring accessories as to SCHNEIDER ELECTRIC Manufacture or approved equivalent. | Set | 1 | 15208.3333 | 15208.3333
LV POWER/RETICULATION/DISTRIBUTION SYSTEM CONT'D
LV POWER/RETICULATION/DISTRIBUTION CABLES
NOTES:
i) | To be supplied and installed c/w all necessary fixing/clipping/supporting/termination accessories as per general specification
ii) | The rate shall cover excavation, sand-bedding,backfilling, trenching e.t.c, and all manholes, where necessary, and all associated builders' works
iii) | All cables are to be as per general specification and type-approved by the supervising Electrical Consultant
B | 600/1000V 95mm sq 4-Core armoured copper cables connected from the 250A MCCB (in Item A above) in Main Distribution Board (MDB) and terminated on to the incomer 250A TPN MCCB Circuit Breaker Power Factor Correction Unit, as per drawings, c/w all necessary connecting accesories (Provisional Total Route length) | L/m | 15 | 104.8308 | 1572.4625
C | ENGINEER'S FACTORY TESTS/INSPECTION
| Allow a provisional sum of supervising Engineers and Employer's personnel to witness the factory tests/inspection for the Power Factor Correction Bank before dispatch. | Item | 1 | 3802.0833 | 3802.0833
D | POWER FACTOR CORRECTION BANK EARTHING SYSTEM:
| Earth the Power Factor Correction Bank as per regulations and code of practice so as to achieve a final earth resistance value NOT exceeding 1.00 Ohm. | Item | 1 | 1140.625 | 1140.625
| ROCA SITE urinal set with one bowl for one person No. 359601000 complete with built-in water supply with fixing set, waste pipe, flexible tube, elbow joint and connector and plastic bottle trap c/w ROCA URINAL flush valve with straight discharge pipe as ROCA Gem No. 526900710 or approved equivalent | No | 1 | 1200 | 1200
| Total cost of the Modifications |  |  |  | 26326.3657

## Light Fittings
COMPLETION OF COFFEE ANALYTICAL LABORATORY &REGIONAL OFFICES AT RUKOKI KASESE
SCHEDULE OF MATERIALS-LIGHTING FITTINGS
UCDA
Item | Description & Specification | Image
A | Suspended self-contained emergency exit sign |  | `
B | Circular LED Recessed Downlight lminaire with Structure material:
C | 1200mm high performance IP65 dust and moisture resistant luminaire for aggressive atmospheres. For 1x36W T26 lamp(s)
D | 1200mm high performance IP65 dust and moisture resistant luminaire for aggressive atmospheres. For 2x36W T26 lamp(s)
E | 18W, round bulkhead luminaire with 1032lm LED package. Electronic, fixed output control gear with 3 hour, manual test, emergency lighting circuit.
F | 350mm∅ Standard circular surface luminaire with Nickel Satin finish
G | Suspended weather resistant decorative bronze finish with 3x60W LED lamps
H | 230mm∅ Circular LED downlight for recessed installation with Structure material: Injected alminium, Structure finish: White, Diffuser material:
I | 600x600mm, 36W recessed LED luminare with a slim 12mm profile.
J | 36W Outdoor Flood Lights
K | 13W , IP20 value performance, low height, ceiling recessed LED downlight.
L | Bulkheads at Gate houses
M | Staircase bulkhead
N | Bathroom/Toilet area bulkhead
O | Double arm Outdoor street lighting on 7m high pole

## Wiring Accessories
COMPLETION OF ANALYTICAL LABORATORY & REGIONAL OFFICES AT RUKOKI KASESE
SCHEDULE OF MATERIALS-WIRING ACCESSORIES
Item | Description & Specification | Image
A | 10AX SP 1-Gang 1-Way white moulded plate switches c/w flush mounting box, as to LEGRAND Manufacture Model: Mallia Cat No. 281000 |  | `
B | 10AX SP 1-Gang 2-Way white moulded plate switches c/w flush mounting box, as to LEGRAND Manufacture Model: Mallia Cat No. 281001.
C | 10AX SP 2-Gang 1-Way white moulded plate switches c/w flush mounting box, as to LEGRAND Manufacture Model: Mallia Cat No. 281002.
D | 10AX SP 2-Gang 2-Way white moulded plate switches c/w flush mounting box, as to LEGRAND Manufacture Model: Mallia Cat No. 281003.
E | 10AX SP 1-Gang Intermediate white moulded plate switches c/w flush mounting box, as to LEGRAND Manufacture Model: Mallia Cat No. 281008.
13A SP 2-Gang white switched socket outlets c/w neon indicator and flush/trunking mounting box, as to to LEGRAND Manufacture Model: Belanko Cat No. 617047
13A SP 2-Gang Non-Standard white switched socket outlets c/w neon indicator and flush mounting box, as to MK Manufacture
20AX DP Switch marked Water Heater/Hand dryer/AC with neon indicator and flush mounting box, as to LEGRAND Manufacture Model: Mallia Cat No. 281061
2 module Quadplexer (TV, FM, Sat1 & Sat 2) Outlet as to Crabtree Cat No. 7066

## FD
COMPLETION OF COFFEE ANALYTICAL LABORATORY & REGIONAL OFFICES AT RUKOKI KASESE
SCHEDULE OF MATERIALS- FIRE DETECTION AND ALARM SYSTEM
UCDA
Item | Description & Specification | Image
A | Addressable Photo detector c/w detector base B501AP, without flange all as to Honeywell Manufacture MI-PSE-S2-IV
B | Addressable Rate-of-Rise Thermal detector c/w detector base B501AP all as to Honeywell Manufacture MI-RHSE-S2-IV
C | Addressable manual call point c/w surface back box SR1T/O for as to Honeywell Manufacture MI-MCP-FLEX
D | Addressable Intelligent Wall Mounted Sounder, Red with Pure White Skirt as to Honeywell Manufacture MI-WSO-PR-N
E | Addressable Wall Mounted Strobe, Red with Pure White Skirt as to Honeywell Manufacture MI-WSS-PR-N
A | DXc2 Loop expansion card Control Panel for (no zone LEDs) 230Vac c/w KIT DXc Network Card powerful I/O features to Honeywell Manufacture 714-001-242 ,
B | Morley Active Repeater Fire Alarm Control Panel for networking c/w powerful I/O features to Honeywell Manufacture 709-601-001

## LPS
COMPLETION OF COFFEE ANALYTICAL LABORATORY &REGIONAL OFFICES AT RUKOKI KASESE
SCHEDULE OF MATERIALS- LIGHTNING PROTECTION SYSTEM
SANDHBOLT
Item | Description & Specification | Image
A | Lighting rod INGESCO PDC mod. E-30 REF.102005
B | Adapter head mast 1'1/2" REF.111012
C | MAST TELESCOPE Steel galvanised 5,8m.2 sections 1'1/2" + 1'1/4 REF.114065
D | T connection (2 pieces) REF.115056
E | Braided Copper Cable (50mm2 REF.117072
F | Insulator claping bracket M8 REF.118106
G | Galvinised Steel Tube REF.119106
C | Test Joint in access box (2 terminals) REF.250004
D | C connection REF.10026
E | Electrode ground rod connection - 14mm REF.115055
F | Copper - plated steel grounding rods 2m x 14mm REF.252029

## CCTV schedule
COMPLETION OF COFFEE ANALYTICAL LABORATORY &REGIONAL OFFICES AT RUKOKI AT KASESE
SCHEDULE OF MATERIALS- CCTV
SANDHBOLT
Item | Description & Specification | Image
A | Dome Camera IP66 Vandal Resistant Dome Housing, 12VDC/24VAC/PoE, Auto focus,Motorized,ONVIF S conformant, IP66 Vandal Resistant Dome Housing, 12VDC / 24VAC /PoE, Auto focus, Motorized as HIK or equal and approved
G | 6Mpx Bullet camera, with integrated lens and IR , IP66 vandal resistant Dome Housing, H.264 compression technology, Auto focus,Motorized as HIK or equal and approved
H | 2RU Digital Sentry NVR with 6TB Expandable to 1TB Storage capacity DSSRV-RD-040-UK
J | 54 Inch Industrial smart LED Monitor c/w Bracket for mounting PMCL542BL
K | 1 HP 280 g3 CORE i3 DESKTOP COMPUTER SET Intel® core i3 processor G4400, Intel HD Graphics 510 (3.3 GHz, 3 MB cache, 2 cores),I Intel®, H11,Microtower, 4 GB DDR4-2133 SDRAM, 2 TB HARD DISK 7200 rpm SATA, SATA SuperMulti DVD writer as HP PC

## General spec
COMPLETION OF COFFEE ANALYTICAL LABORATORY &REGIONAL OFFICE AT RUKOKI KASESE PHASE 02:
ELECTRICAL INSTALLATION - BILLS OF QUANTITIES
Item | Description and Specification
ELECTRICAL INSTALLATIONS
ALL SPECIFIED MATERIALS-GENERAL NOTES
i) | To be supplied, delivered to site, installed, connected complete and commissioned in full working condition including all fixing/mounting/terminatinf accessories as per Specificationof the Electrical Engineer.
ii) | All electrical items to be suitable for 415/240V power system
iii) | All power supply cables and power line construction materials measured under this Bills of Quantities are provisional. Actual measurements will be done on site during evaluation.
iv) | All underground reticulation and distribution cables are to be supplied c/w all necessary fixing/clipping/supporting/termination accessories as per general specification and approved by supervising Electrical Consultant.
v) | The rate for the underground cables shall cover excavation, sand-bedding, backfilling, trenching, enclosing in PVC ducts, etc and all manholes, where necessary, and all associated builders' works. Actual measurements shall be based on the site conditions.
vi) | All indoor cables are to be recessed within the wall fabric and are to be enclosed in suitably sized PVC conduits neatly installed and to further Instructions form the Electrical Engineer and/or Drawings.
vii) | All lighting fittings to be as per Drawings with control gear compartible with 240/50Hz. All fluorescent fittings are to have electronic ballasts. All lighting fittings are to be approved by the Engineer, prior to installation.
viii) | All wiring accessories to be of flush mounting and approved Legrand / Thorn or approved manufacture. The items are to be complete with all necessary fixing, mounting accessories and MK boxes. Samples to be apporved prior to installation by Engineer.
ix) | The entire electrical installation shall be tested for compliance in accordance to the 17th Edition of of the IEE Wiring Regulations and witnessed/approved by the Engineer
x) | All Distribution boards to be of ABB/ Scheneider Electric/Crabtree/Legrand Manufacture, or approved equivalent
xi) | The Control Gear for ALL Fluorescent lamps shall consist of ELECTRONIC BALLAST for power factor correction to better than 0.9 lagging. The lamps shall be non-flicker and suitable for operation within 160V to 250V range, efficient and energy saving, and as per General Specification hereof.

## MAINS POWER SUPPLY
COMPLETION OF COFFEE ANALYTICAL LABORATORY &UCDA REGIONAL OFFICES AT RUKOKI KASESE.
ELECTRICAL INSTALLATION - BILLS OF QUANTITIES
Item | Description and Specification | Unit | Qty | Rate (UGX) | Amount (UGX) | Rate (Ugx)
MAINS POWER SUPPLY
ALL SPECIFIED MATERIALS:
To be supplied, transported to site, connected up complete and commissioned in full working conditions including all necessary fixing/mounting accessories.
All items shall be as per "General" and "Particular" Specification and Drawings.
UMEME LTD. MAINS POWER SUPPLY
A | Allow a Provisional Sum of Ugx 10,000,000 to liaise with UMEME Ltd. Authorities for extension of 3-phase 33kV power to the premises c/w 35mm sq 3-Core XLPE- SWA-PVC-11kV (MV) Copper Cable and 3-phase MV metering unit & protection system. | Sum
EL-1 | TOTAL TO SUMMARY PAGE |  |  |  | 0
MAIN LOW VOLTAGE DISTRIBUTION BOARD
Note : Contractor to submit the manufacturer's technical
Specification and working drawings for the Engineer's
approval before purchase:
A | 200A, 415V, 6-Way TPN MCCB-type Main LV Distribution board (MDB - on Ground Floor), MCCB type as to CRABTREE/SCHNEIDER ELECTRIC BLOCKSET Manufacture, or approved equivalent, as per specifications and drawing, and complete with, but not limited, to the under-listed: | Set | 1 |  |  | 20128500
i) 1 x 200A TP MCCB-incoming
ii) 2No.x 100A TP MCCB-outgoing
iii) 3No.x 63A TP MCCB-outgoing
iv) 1No. TP Spareway
B | MAIN LOW VOLTAGE SWITCHBOARD EARTHING SYSTEM:
| Earth the Main Low Voltage Switch Board as per regulations and code of practice so as to achieve a final earth resistance value NOT exceeding 1.00 Ohm.. | Item | 1 |  |  | 783900
C | Metalcased with lockable hinged door 8-Way TPN MCB-type flush mounted Distribution Board (DB1) complete with 100A TP main integral isolator switch, busbars,neutral and earth terminal blocks, c/w 6No. x 10A SP MCBs, 6No. x 32A SP MCBs, 3No. x 20A SP MCBs, 1No. x 63A TP MCCBs and 6No. x SP Spareways with Blanking Plates as per specifications and drawing, all as to SCHENEIDER ELECTRIC manufacture or approved equivalent | Set | 1
D | Metalcased with lockable hinged door 6-Way TPN MCB-type flush mounted Distribution Board (DB2) complete with 100A TP main integral isolator switch, busbars,neutral and earth terminal blocks, c/w 6No. x 10A SP MCBs, 5No. x 32A SP MCBs, 2No. x 20A SP MCBs, and 5No. x SP Spareways with Blanking Plates as per specifications and drawing, all as to SCHENEIDER ELECTRIC manufacture or approved equivalent | Set | 1
E | Metalcased with lockable hinged door 4-Way TPN MCB-type flush mounted Distribution Board (DB-AC, & DB-AC1) complete with 63A TP main integral isolator switch, busbars,neutral and earth terminal blocks, c/w 9No. x 32A SP MCBs, and 3No. x SP Spareways with Blanking Plates as per specifications and drawing, all as to SCHENEIDER ELECTRIC manufacture or approved equivalent | Set | 2
F | Metalcased with lockable hinged door 4-Way TPN MCB-type flush mounted Distribution Board (DB-G) for general areas complete with 63A TP main integral isolator switch, busbars,neutral and earth terminal blocks, c/w 2No. x 32A TP MCCBs, 2No. x 20A SP MCBs, 1No.x16A SP MCB and 3No. x SP Spareways with Blanking Plates as per specifications and drawing, all as to SCHENEIDER ELECTRIC manufacture or approved equivalent | Set | 1
MAINS POWER SUPPLY CONT'D :LOW VOLTAGE POWER DISTRIBUTION CABLES
NOTES:
i) | To be supplied and installed c/w all necessary fixing/clipping/supporting/termination accessories as per general specification
ii) | The rate shall cover excavation, sand-bedding,backfilling, trenching e.t.c, and all manholes, where necessary, and all associated builders' works
iii) | All cables are to be as per general specification and type-approved by the supervising Electrical Engineer
A | 1Run x 70mm sq 4Core armoured copper cables connected from the LV side of the UMEME Feeder Pillar and terminated on to the incomer 200A TPN circuit breaker of the change over switch, as per drawings, c/w all necessary connecting accesories (Provisional Route length) | L/m | 20 |  |  | 2916000
B | 1Run x 70mm sq 4Core armoured copper cables connected from the outgoing side of the chamge over switch and terminated on to the incomer 200A TPN circuit breaker of the MDB, as per drawings, c/w all necessary connecting accesories (Provisional Route length) | L/m | 5 |  |  | 2916000
C | Allow for 35mm, 25mm, 16mm sq 4C cables from the MDB to the respective distribution boards as per the wiring diagrams | PS | 1
EL-2 | CARRIED FORWARD
COLLECTION PAGE FOR MAINS POWER SUPPLY/RETICULATION AND DISTRIBUTION
FROM PAGE EL-1
FROM PAGE EL-2
EL-3 | TOTAL TO SUMMARY PAGE

## STANDBY POWER SUPPLY
PROPOSED UCDA REGIONAL OFFICE & ANALYTICAL LABORATORY IN KASESE
ELECTRICAL INSTALLATION - BILLS OF QUANTITIES
Item | Description and Specification | Unit | Qty | Rate (UGX) | Amount (UGX) | Rate (Ugx)
STANDBY POWER SUPPLY
ALL SPECIFIED MATERIALS:
To be supplied, transported to site, connected up complete and commissioned in full working conditions including all necessary fixing/mounting accessories.
STANDBY GENERATOR SET & ASSOCIATED WORKS
A | 125kVA 50Hz, 415/240V 3-Phase diesel engine generator set c/w fixing and mounting accessories, testing and commissioning to the satisfaction of the Electrical Engineer, c/w sound-weather proofing canopy, base-frame fuel tank for 8-hour duty and all the necessary exhaust and hot air ducting; as to CATERPILLAR. manufacture, or approved equivalent. | Set | 1 |  |  | 230949457
B | Earth the Generator sets as per IEE regulations and code of practice, so as to achieve a final earth resistance value NOT exceeding 1.00 Ohm. | Item | 1 |  |  | 783900
LOW VOLTAGE POWER DISTRIBUTION CABLES
NOTES:
i) | To be supplied and installed c/w all necessary fixing/clipping/supporting/termination accessories as per general specification
ii) | The rate shall cover excavation, sand-bedding,backfilling, trenching e.t.c, and all manholes, where necessary, and all associated builders' works. All cables are to be as per general specification and type-approved by the supervising electrical engineer
A | 1Run x 70mm sq 4Core armoured copper cables connected from the LV side of the Generator side and terminated on to the incomer 200A TPN circuit breaker of the change over switch, as per drawings, c/w all necessary connecting accesories (Provisional Route length) | L/m | 10 |  |  | 2916000
CABLE MANAGEMENT
B | Allow for a 150mmØ uPVC, Heavy Duty, High Density Sleeves | L/m | 8 |  |  | 4950000
C | 50mmØ uPVC, Heavy Duty, High Density Sleeves | L/m | 5 |  |  | 4950
D | 800mm (Length) x 6000mm (width) x 600mm (depth) cable draw man hole complete with a water tight heavy duty manhole cover all as to Electrical Engineers guidance and to the Civil/Structural Engineer's Detail and satisfaction | No. | 2 |  |  | 768600
EL-4 | TOTAL TO SUMMARY PAGE

## Main Block
COMPLETION OF COFFEE ANALYTICAL LABORATORY &UCDA REGIONAL OFFICES AT RUKOKI KASESE.
ELECTRICAL INSTALLATION - BILLS OF QUANTITIES
Item | Description and Specification | Unit | Qty | Rate (UGX) | Amount(UGX) | Rate (Ugx)
GROUND FLOOR
LIGHTING FITTINGS
ALL SPECIFIED MATERIALS:
To be supplied, transported to site, connected up complete and commissioned in full working conditions including all necessary fixing/mounting accessories.
A | '600mmx600mm 50W Recessed mounted LED luminaire louvrefitting with built in driver and diffuser for direct / indirect lighting performance asFitzgerald LED Celestial Cat no. CE50/B/CO/850 or equal and approved equivalent (Offices). | No. | 30
B | Dito bu surface louvre fittings | No. | 20
B | Basic Warm Light Flourescent luminaire for 2 x 18W lamps. Integral high frequency electronic ballast. Body compression moulded glass reinforced polyester (GRP), light grey colour. Enclosure injection moulded prismatic clear, UV stabilised, polycarbonate. Enclosure retained to body by stainless steel toggle clips. IP65 to IEC529 as to Thorn Manufacture or approved equivalent. | No. | 2 |  |  | 291150
C | Ditto light but 1 x 18W lamps | No. | 14 |  |  | 291150
D | Recessed mounted Downlight c/w die cast aluminium housing, clear front glass and electronic gear with neutral white light in 18W as to LED C4 Equal L or equal and approved equivalent. (Corridors, reception and coffee bar counter) | No. | 14 |  |  | #REF!
E | Suspended self-contained emergency exit sign using LED with white stove enamelled aluminium extrusion body with white polycarbonate end caps, suitable for interior use for non-maintained emergency application of 3 hour duration. As Thorn Voyager LED or approved equivalent | No. | 4 |  |  | 297000
F | 226W, highly efficient, general purpose, LED area floodlight, for outdoor Lighting as per the drawing all as to THORN Manufacture or approved equivalent.(open courtyard area) | No. | 2 |  |  | 768600
G | 20W surface mounted LED luminaire c/w integrated LED driver, IP65 die cast aluminium as to Fitzgerald LED Legion Cat No. LEGR20/CO/850 or equal and approved equivalent. (Entrance Canopy) | No. | 4
H | 195mmØ recessed ceiling downlight in white paint finish c/w 23W LED with IP65 rating sealed bezel for the glass and an output driver as to Fitzgerald LED Circulux Cat No. CIR23/CO/840 or approved equivalent (Washrooms) | No. | 20
I | Suspended 1 x 40W LED lamp in Vandal resistant diecast Alminium Body as to FITZGERALD or approved equivalent.(Agro input stores) | No. | 15
J | Suapended Decorative Pendant with 3 12W lamps LED SAMSUNG color temperature LED warm light 2700K light complete to IP20 as THORN or approved equal (cafeteria area and outdoor sitting space) | No. | 7
EL-5 | TOTAL FOR LIGHTING FITTINGS TO COLLECTION PAGE
WIRING ACCESSORIES. ALL SPECIFIED MATERIALS
To be transported to site, connected up complete and commissioned in full working conditions including all necessary fixing/mounting accessories.
A | 10AX SP 1-Gang 1-Way white moulded plate switches c/w flush mounting box, as to LEGRAND Manufacture Model: Mallia Cat No. 281000, or approved equivalent. | No. | 17 |  |  | 31950
B | 10AX SP 2-Gang 1-Way white moulded plate switches c/w flush mounting box, as to LEGRAND Manufacture Model: Mallia or approved equivalent. | No. | 3 |  |  | 31950
C | 10AX SP 3-Gang 1-Way white moulded plate switches c/w flush mounting box, as to LEGRAND Manufacture Model: Mallia or approved equivalent. | No. | 3 |  |  | 31950
D | 10AX SP 1-Gang 2-Way white moulded plate switches c/w flush mounting box, as to LEGRAND Manufacture Model: Mallia or approved equivalent. | No. | 18 |  |  | 31950
E | 13A SP 2-Gang white switched socket outlets c/w neon indicator and flush/trunking mounting box, as to to LEGRAND Manufacture Model: Belanko Cat No. 617047 or approved equivalent | No. | 38 |  |  | 48600
F | 20AX DP Switch marked Hand dryer/AC with neon indicator and flush mounting box, as to LEGRAND Manufacture Model: Mallia Cat No. 281061 or approved equivalent | No. | 17 |  |  | 43650
G | IP44 32A TPN 3P+N+E 1-Gang white panel mounting inclined industrial socket outlets and flush mounting box, as to LEGRAND List No. 555189, or approved equivalent | No. | 2 |  |  | 201600
H | 24-Hour programme time switch c/w fixing accessories and back-up battery (150 hours) and 20A contactor, as to LEGRAND List No. 49951, or equivalent, including a suitable enclosure. | No. | 1 |  |  | 432000
I | 2 Way Co-axial UHF, VHF sockect outlet complete with flush mounting box as Crabtree List No.7268, or approved equivalent. | No. | 1
J | Profile 201, 220mm x 65mm, 3-Compartment prestige skirting and DADO trunking(for data, telephone and power socket outlets), complete with all necessary accessories such as couplers, end caps, internal bends, external bends, flat angles, flat tees, e.t.c.; all as to MARSHALL-TUFFLEX manufacture, or approved equivalent (Provisional total cable length). | LM | 120
EL-6 | TOTAL TO COLLECTION PAGE
WIRING
Lighting points:
A | All Lighting points in office areas to be connected complete and ready from 10A/16A SP miniature circuit breakers of consumer unit, using 2.5mm² SC PVC-Insulated copper cables in radial circuits, drawn in uPVC flush conduits, through walls/switches/time switch, as per drawings. | No. | 135 |  |  | 140400
Raw Power points:
C | Power points to be connected complete and ready from 32A SP miniature circuit breakers of of the repective Distribution Boards , using 2.5mm² SC PVC-Insulated stranded copper cables in ring circuits, drawn in uPVC flush installed conduits,as per drawings. | No. | 40 |  |  | 153360
Industrial Socket power Points
F | To be connected complete and ready from 32A TP miniature circuit breakers of the repective Distribution Boards, using 6mm² 4-Core XLPE-SWA-PVC-Insulated Copper Cables in radial circuits, drawn in uPVC on cable tray/ uPVC flush installaed Conduits, as per drawings. | No. | 2 |  |  | 396000
Hand Dryer Points:
| All wiring of hand dryer points to be connected complete and ready from 20A SP miniature circuit breakers of consumer unit, in 2.5mm sq. SC PVC-Insulated stranded copper cables in radial circuits, drawn in uPVC flush installed conduits, , as per drawings | No. | 7
Air Conditioning Points & Terrace extract Fan
| All wiring of Air conditioning points to be connected complete and ready from 20A/32A SP miniature circuit breakers of consumer units, in 2.5mm sq. SC PVC-Insulated stranded copper cables in ring circuits, drawn in uPVC flush installed conduits, , as per drawings. | No. | 9
Ceiling Fans Points:
| All wiring of Air conditioning points to be connected complete and ready from 20A SP miniature circuit breakers of consumer units, in 2.5mm sq. SC PVC-Insulated stranded copper cables in ring circuits, drawn in uPVC flush installed conduits, , as per drawings. | No. | 5
Hosereel pump
| All wiring of Pumps to be connected complete and ready from 32A TP miniature circuit breakers of consumer units, in 4mm sq. SC PVC-Insulated stranded copper cables in ring circuits, drawn in uPVC flush installed conduits, , as per drawings. | No. | 2
EL-7 | TOTAL TO COLLECTION PAGE
COLLECTION PAGE FOR GROUND FLOOR
FROM PAGE EL-5
FROM PAGE EL-6
FROM PAGE EL-7
EL-8 | TOTAL TO SUMMARY PAGE
FIRST FLOOR
LIGHTING FITTINGS
ALL SPECIFIED MATERIALS:
To be supplied, transported to site, connected up complete and commissioned in full working conditions including all necessary fixing/mounting accessories.
A | '600mmx600mm 50W Recessed mounted LED luminaire with built in driver and diffuser for direct / indirect lighting performance asFitzgerald LED Celestial Cat no. CE50/B/CO/850 or equal and approved equivalent (Offices). | No. | 30
B | Basic Warm Light Flourescent luminaire for 2 x 18W lamps. Integral high frequency electronic ballast. Body compression moulded glass reinforced polyester (GRP), light grey colour. Enclosure injection moulded prismatic clear, UV stabilised, polycarbonate. Enclosure retained to body by stainless steel toggle clips. IP65 to IEC529 as to Thorn Manufacture or approved equivalent. | No. | 10 |  |  | 291150
C | Ditto light but 1 x 18W lamps | No. | 2 |  |  | 291150
D | Recessed mounted Downlight c/w die cast aluminium housing, clear front glass and electronic gear with neutral white light in 18W as to LED C4 Equal L or equal and approved equivalent. (Corridor) | No. | 13 |  |  | #REF!
E | 226mmØ circular recessed luminaire c/w 25W LED with a driver and IP54 rated diffuser glass cover with a 3hr remote sustained emergency as to Fitzgerald LED Ghost Cat No. GHO25/CO/865/RLS3 or approved equivalent (Reception lobby void) | No. | 12
F | Suspended self-contained emergency exit sign using LED with white stove enamelled aluminium extrusion body with white polycarbonate end caps, suitable for interior use for non-maintained emergency application of 3 hour duration. As Thorn Voyager LED or approved equivalent | No. | 1 |  |  | 297000
G | 195mmØ recessed ceiling downlight in white paint finish c/w 23W LED with IP65 rating sealed bezel for the glass and an output driver as to Fitzgerald LED Circulux Cat No. CIR23/CO/840 or approved equivalent (Washrooms) | No. | 8
H | Basic weather resistant LED bulkheads as to Fitzegerald for staircase lighting as approved( for all floors staircase lighting) | No. | 4
EL-9 | TOTAL FOR LIGHTING FITTINGS TO COLLECTION PAGE
WIRING ACCESSORIES. ALL SPECIFIED MATERIALS
To be transported to site, connected up complete and commissioned in full working conditions including all necessary fixing/mounting accessories.
A | 10AX SP 1-Gang 1-Way white moulded plate switches c/w flush mounting box, as to LEGRAND Manufacture Model: Mallia Cat No. 281000, or approved equivalent. | No. | 12 |  |  | 31950
B | 10AX SP 2-Gang 1-Way white moulded plate switches c/w flush mounting box, as to LEGRAND Manufacture Model: Mallia or approved equivalent. | No. | 4 |  |  | 31950
C | 10AX SP 1-Gang 2-Way white moulded plate switches c/w flush mounting box, as to LEGRAND Manufacture Model: Mallia or approved equivalent. | No. | 10 |  |  | 31950
D | 13A SP 2-Gang white switched socket outlets c/w neon indicator and flush/trunking mounting box, as to to LEGRAND Manufacture Model: Belanko Cat No. 617047 or approved equivalent | No. | 40 |  |  | 48600
E | 20AX DP Switch marked Hand dryer/AC with neon indicator and flush mounting box, as to LEGRAND Manufacture Model: Mallia Cat No. 281061 or approved equivalent | No. | 15 |  |  | 43650
F | Profile 201, 220mm x 65mm, 3-Compartment prestige skirting and DADO trunking(for data, telephone and power socket outlets), complete with all necessary accessories such as couplers, end caps, internal bends, external bends, flat angles, flat tees, e.t.c.; all as to MARSHALL-TUFFLEX manufacture, or approved equivalent (Provisional total cable length). | lm | 120
EL-10 | TOTAL TO COLLECTION PAGE
WIRING
Lighting points:
A | All Lighting points in office areas to be connected complete and ready from 10A/16A SP miniature circuit breakers of consumer unit, using 2.5mm² SC PVC-Insulated copper cables in radial circuits, drawn in uPVC flush conduits, through walls/switches/time switch, as per drawings. | No. | 80 |  |  | 140400
Raw Power points:
C | Power points to be connected complete and ready from 32A SP miniature circuit breakers of of the repective Distribution Boards , using 2.5mm² SC PVC-Insulated stranded copper cables in ring circuits, drawn in uPVC flush installed conduits,as per drawings. | No. | 30 |  |  | 153360
Hand Dryer Points:
| All wiring of hand dryer points to be connected complete and ready from 20A SP miniature circuit breakers of consumer unit, in 2.5mm sq. SC PVC-Insulated stranded copper cables in radial circuits, drawn in uPVC flush installed conduits, , as per drawings | No. | 4
Air Conditioning Points
| All wiring of Air conditioning points to be connected complete and ready from 20A/32A SP miniature circuit breakers of consumer units, in 2.5mm sq. SC PVC-Insulated stranded copper cables in ring circuits, drawn in uPVC flush installed conduits, , as per drawings. | No. | 8
Ceiling Fans Points:
| All wiring of Air conditioning points to be connected complete and ready from 20A SP miniature circuit breakers of consumer units, in 2.5mm sq. SC PVC-Insulated stranded copper cables in ring circuits, drawn in uPVC flush installed conduits, , as per drawings. | No. | 2
EL-11 | TOTAL TO COLLECTION PAGE
COLLECTION PAGE FOR FIRST FLOOR
FROM PAGE EL-9
FROM PAGE EL-10
FROM PAGE EL-11
EL-12 | TOTAL TO SUMMARY PAGE
SECOND FLOOR
LIGHTING FITTINGS
ALL SPECIFIED MATERIALS:
To be supplied, transported to site, connected up complete and commissioned in full working conditions including all necessary fixing/mounting accessories.
A | Basic Warm Light Flourescent luminaire for 1 x 18W lamps. Integral high frequency electronic ballast. Body compression moulded glass reinforced polyester (GRP), light grey colour. Enclosure injection moulded prismatic clear, UV stabilised, polycarbonate. Enclosure retained to body by stainless steel toggle clips. IP65 to IEC529 as to Thorn Manufacture or approved equivalent. | No. | 3 |  |  | 291150
WIRING ACCESSORIES.
To be transported to site, connected up complete and commissioned in full working conditions including all necessary fixing/mounting accessories.
B | 10AX SP 1-Gang 1-Way white moulded plate switches c/w flush mounting box, as to LEGRAND Manufacture Model: Mallia Cat No. 281000, or approved equivalent. | No. | 2 |  |  | 31950
WIRING
Lighting points:
C | All Lighting points in office areas to be connected complete and ready from 10A/16A SP miniature circuit breakers of consumer unit, using 2.5mm² SC PVC-Insulated copper cables in radial circuits, drawn in uPVC flush conduits, through walls/switches/time switch, as per drawings. | No. | 3 |  |  | 140400
EL-13 | COLLECTION FOR SECOND FLOOR TO SUMMARY PAGE
SUMMARY PAGE
GROUND FLOOR PAGE EL- 8
FIRST FLOOR PAGE EL- 12
SECOND FLOOR PAGE EL- 13
EL-14 | TOTAL FOR MAIN BLOCK TOMAIN SUMMARY PAGE

## FF (hidden)
PROPOSED LABOREX MANUFACTURING, STORAGE AND DISTRIBUTION FACILITY ON PLOT 909, NAMANVE INDUSTRIAL PARK, MUKONO DISTRICT
ELECTRICAL INSTALLATION - BILLS OF QUANTITIES
Electrical Drawings Nos:
Item | Description and Specification | Unit | Qty | Rate (USD) | Amount (USD) | Rate (Ugx)
FIRST FLOOR
LV POWER/RETICULATION/DISTRIBUTION SYSTEM
SUB-MAIN DISTRIBUTION BOARDS:
Note: Contractor to submit the manufacturer's specification and working drawings for the Engineer's approval before purchase
A | Metalcased with lockable hinged door 6-Way TPN MCB-type flush mounted Distribution Board (DB-AC3) complete with 100A TP main integral isolator switch, busbars,neutral and earth terminal blocks, c/w 12No. x 20A SP MCBs and 6No. x SP Spareways with Blanking Plates as per specifications and drawing, all as to SCHENEIDER ELECTRIC manufacture or approved equivalent | Set | 1 | #REF! | #REF! | #REF!
B | Metalcased with lockable hinged door 8-Way TPN MCB-type flush mounted Distribution Board (DB-AC3) complete with 125A TP main integral isolator switch, busbars,neutral and earth terminal blocks, c/w 18No. x 20A SP MCBs and 6No. x SP Spareways with Blanking Plates as per specifications and drawing, all as to SCHENEIDER ELECTRIC manufacture or approved equivalent | Set | 1 | 710 | 710 | 2556000
C | Metalcased with lockable hinged door 8-Way TPN MCB-type flush mounted Distribution Board (DB-2) complete with 100A TP main integral isolator switch, busbars,neutral and earth terminal blocks, c/w 5No. x 10A SP MCBs, 3No. x 32A SP MCBs, 2No. x 20A SP MCBs and 8No. x SP Spareways with Blanking Plates as per specifications and drawing, all as to SCHENEIDER ELECTRIC manufacture or approved equivalent | Set | 1 | 710 | 710 | 2556000
D | Metalcased with lockable hinged door 6-Way TPN MCB-type flush mounted Distribution Board (UP/DB-M) complete with 100A TP main integral isolator switch, busbars,neutral and earth terminal blocks, c/w 1No. x 50A TP MCB, 1No. x 50A SP MCB, 1No. x 63A TP MCBand 3No. x TP Spareways with Blanking Plates and 1No. x SP Spareway with blanking plates as per specifications and drawing, all as to SCHENEIDER ELECTRIC manufacture or approved equivalent | Set | 1 | #REF! | #REF! | #REF!
E | Metalcased with lockable hinged door 100A; 12-Way SPN MCB-TYPE Distribution Board (UP/DB-2), c/w 3No. X 32A x MCBs x SP Spare way blanking plates,all as to SCHENEIDER ELECTRIC manufacture or approved equivalent (UPS Board) | No. | 1 | 215 | 215 | 774000
EL-19 | TOTAL TO COLLECTION PAGE |  |  |  | #REF!
FIRST FLOOR
UNINTERRUPTIBLE POWER SUPPLY (UPS) UNIT:
NOTES:
i) | To be supplied and installed c/w all necessary fixing/clipping/supporting/termination accessories as per general specification
A | 30kVA, 3-Phase Uninterruptible Power Supply (UPS-1) unit with Input: (Voltage 380V -415V 3-Phase), Frequency: (45Hz -65Hz), Input Current Total Harmonic Distortion (THDI < 4.5% with THM and PFC filter); Output: Voltage (240V, 1-Phase), Frequency (50Hz), Overload (100% - 110% for 10 minutes), Efficiency (98%); Batteries: Back-up time (10-120 minutes), Type (Maintenance free VRLA Batteries); all as to EATON UPS Systems, or approved equivalent. | No | 1 | 19525 | 19525 | 70290000
B | UNINTERRUPTIBLE POWER SUPPLY (UPS) UNIT EARTHING SYSTEM:
| Earth the Voltage Stabilizer as per regulations and code of practice. | Item | 1 | 292.875 | 292.875 | 1054350
EL-20 | TOTAL TO COLLECTION PAGE |  |  |  | 19817.875
FIRST FLOOR
LV POWER/RETICULATION/DISTRIBUTION SYSTEM CONT'D
LV POWER/RETICULATION/DISTRIBUTION CABLES
NOTES:
i) | To be supplied and installed c/w all necessary fixing/clipping/supporting/termination accessories as per general specification
ii) | The rate shall cover excavation, sand-bedding,backfilling, trenching e.t.c, and all manholes, where necessary, and all associated builders' works
iii) | All cables are to be as per general specification and type-approved by the supervising Electrical Consultant
A | 600/1000V 25mm sq 4-Core XLPE-SWA-PVC-I copper cables connected from the Sub-Main Distribution Board (SMDB-1) and terminated onto the 100A Integral Isolator of Distribution Board (DB-AC2) as per drawings, c/w all necessary connecting accessories (Provisional Route Length). | L/m | 60 | #REF! | #REF! | #REF!
B | 600/1000V 35mm sq 4-Core XLPE-SWA-PVC-I copper cables connected from the Sub-Main Distribution Board (SMDB-1) and terminated onto the 125A Integral Isolator of Distribution Board (DB-AC3) as per drawings, c/w all necessary connecting accessories (Provisional Route Length). | L/m | 30 | #REF! | #REF! | #REF!
C | 600/1000V 35mm sq 4-Core XLPE-SWA-PVC-I copper cables connected from the Sub-Main Distribution Board (SMDB-1) and terminated onto the 125A Integral Isolator of Distribution Board (DB-3) as per drawings, c/w all necessary connecting accessories (Provisional Route Length). | L/m | 30 | #REF! | #REF! | #REF!
D | 600/1000V 16mm sq 4-Core XLPE-SWA-PVC-I copper cables connected from the Distribution Board (DB-3) and terminated onto the 100A Integral Isolator of Distribution Board (DB-2) as per drawings, c/w all necessary connecting accessories (Provisional Route Length). | L/m | 40 | #REF! | #REF! | #REF!
E | 600/1000V 16mm sq 4-Core XLPE-SWA-PVC-I copper cables connected from the Sub-Main Distribution Board (SMDB-1) and terminated onto the incomer terminals of the 30kVA UPS as per drawings, c/w all necessary connecting accessories (Provisional Route Length). | L/m | 80 | #REF! | #REF! | #REF!
F | 600/1000V 16mm sq 4-Core XLPE-SWA-PVC-I copper cables connected from the outgoingn terminals of the UPS and terminated onto the 100A Integral Isolator of Distribution Board (UP/DB-M) as per drawings, c/w all necessary connecting accessories (Provisional Route Length). | L/m | 10 | #REF! | #REF! | #REF!
G | 600/1000V 16mm sq 3-Core XLPE-SWA-PVC-I copper cables connected from the Distribution Board (UP/DB-M) and terminated onto the 100A; UPS Distribution Board (UP/DB-2) as per drawings, c/w all necessary connecting accessories (Provisional Route Length). | L/m | 30 | 13.125 | 393.75 | 47250
EL-21 | TOTAL TO COLLECTION PAGE |  |  |  | #REF!
FIRST FLOOR
CABLE MANAGEMENT
A | 200mm x 50mm Galvanised Iron Steel Cable Tray, complete with fixing accessories for Power and ICT Cables | L/m | 150 | 14.675 | 2201.25 | 52830
PVC - DADO TRUNKING SYSTEM
B | Profile 201, 220mm x 65mm, 3-Compartment prestige skirting and DADO trunking(for data, telephone and power socket outlets), complete with all necessary accessories such as couplers, end caps, internal bends, external bends, flat angles, flat tees, e.t.c.; | L/m | 400 | #REF! | #REF! | #REF!
LIGHTING FITTINGS
ALL SPECIFIED MATERIALS:
To be transported to site, connected up complete and commissioned in full working conditions including all necessary fixing/mounting accessories.
C | IP65 stylish, robust, wall mounted vandal resistant luminaire with 1 x 40W LED lamp. Material in Vandal resistant diecast Alminium Body with UV stabilized polycarbonate diffuser and all gaskets manufactured from heat resistant silicone rubber to ensure IP65 rating. As to FITZGERALD LED PALADINE SQUARE PALS 40/CO/840 or approved equivalent. | No. | 7 | 80.875 | 566.125 | 291150
D | 1200mm 1x36W Surface mounted single tube high performance IP65 dust and moisture resistant flourescent luminaire in acrylic diffuser with internal prisms c/w T26 lamps, qucik-fix installation brackets as to THORN CORROSION FORCE II CORRF5 1X36W T26 HF L840/840 or approved equivalent. | No. | 2 | 63.75 | 127.5 | 229500
E | Suspended self-contained emergency exit sign using LED with white stove enamelled aluminium extrusion body with white polycarbonate end caps, suitable for interior use for non-maintained emergency application of 3 hour duration. As Thorn Voyager LED or approved equivalent | No. | 6 | #REF! | #REF! | #REF!
F | Powder Coated Steel Trim 1 x 7W LED E27 recessed Downlight as to LAMPTITUDE E-BOX-ADJ | No. | 16 | 61.875 | 990 | 222750
G | IP44,130mm∅ Emergency Circular LED downlight for recessed installation with Structure material: Injected alminium, Structure finish: White, Diffuser material: UVA methacrylate and Diffuser finish: White c/w30 x LED 11W lamp and 3 Hour maintained emergency lighting all as to LEDS-C4 Manufacturer Model: ECOLED 90-1783-14-M3 or approved equivalent. | No. | 4 | #REF! | #REF! | #REF!
H | IP44,130mm∅ Emergency Circular LED downlight for recessed installation with Structure material: Injected alminium, Structure finish: White, Diffuser material: UVA methacrylate and Diffuser finish: White c/w30 x LED 11W lamp all as to LEDS-C4 Manufacturer Model: ECOLED 90-1783-14-M3 or approved equivalent. | No. | 10 | #REF! | #REF! | #REF!
EL-22 | TOTAL TO COLLECTION PAGE |  |  |  | #REF!
FIRST FLOOR
LIGHTING FITTINGS
ALL SPECIFIED MATERIALS:
To be transported to site, connected up complete and commissioned in full working conditions including all necessary fixing/mounting accessories.
A | 600x600mm, 36W recessed LED luminare with a slim 12mm profile. Electronic, fixed out put control gear. Class II electrical,IP 44 from below, IP20 from above, IK02. Body: sheet steel, white (RAL9016). Diffuser: UV stablised opal acrylic. Electrical connection via push wire terminal blocks, loop in/loop out possible. complete with 4000K LED. As Thorn OMEGA LED 3250 HF L830 597 or approved equivalent. | No. | 66 | #REF! | #REF! | #REF!
B | 600x600mm, 36W recessed LED luminare with a slim 12mm profile. Electronic, fixed out put control gear. Class II electrical,IP 44 from below, IP20 from above, IK02. Body: sheet steel, white (RAL9016). Diffuser: UV stablised opal acrylic. Electrical connection via push wire terminal blocks, loop in/loop out possible. complete with 4000K LED . As Thorn OMEGA LED 3250 HF E3 L830 597 or approved equivalent. | No. | 9 | #REF! | #REF! | #REF!
C | A classic batten luminaire for 2 x 58W T26 lamp(s) with electronic -fixed output ballast. IP20, Class I electrical. Batten: white, pre-coated rolled form steel. Endcaps/lamp holders: injection moulded white Polycarbonate (PC). Mounting plates (FixExpress): injection moulded Polycarbonate (PC). 600mm fixing centres. Electrical connection via 4 x 2.5mm² terminal block, all internal wiring is halogen free. Equipped with: A white steel LiteLine reflector for PopPack Pro batten with twin 58W lamps c/w a presence detector and daylight sensor module for all PopPack Pro battens and modules luminaires (except 14W T16) POPPACK SLD KIT and suspension kit. As Thorn POPPACK PRO 2x58W T26 HF L000 | No. | 29 | #REF! | #REF! | #REF!
D | A classic batten luminaire for 2 x 58W T26 lamp(s) with electronic -fixed output ballast. IP20, Class I electrical. Batten: white, pre-coated rolled form steel. Endcaps/lamp holders: injection moulded white Polycarbonate (PC). Mounting plates (FixExpress): injection moulded Polycarbonate (PC). 600mm fixing centres. Electrical connection via 4 x 2.5mm² terminal block, all internal wiring is halogen free. Equipped with: A white steel LiteLine reflector for PopPack Pro batten with twin 58W lamps c/w A presence detector and daylight sensor module for all PopPack Pro battens and modules luminaires (except 14W T16) POPPACK SLD KIT and a standards compliant, 3 hour SelfTest LED emergency conversion module for all PopPack Pro battens and modules luminaires (except 14W T16) POPPACK LED E3T KIT and suspension kit . As Thorn POPPACK PRO 2x58W T26 HF L000 | No. | 17 | #REF! | #REF! | #REF!
E | IP44,230mm∅ Circular LED downlight for recessed installation with Structure material: Injected alminium, Structure finish: White, Diffuser material: UVA methacrylate and Diffuser finish: White c/w 1x LED 20W lamp all as to LEDS-C4 Manufacturer Model: ECOLED 90-1785-14-M3 or approved equivalent. | No. | 39 | #REF! | #REF! | #REF!
F | IP44,230mm∅ Emergency Circular LED downlight for recessed installation with Structure material: Injected alminium, Structure finish: White, Diffuser material: UVA methacrylate and Diffuser finish: White c/w 1x LED 20W lamp and 3 Hour maintained emergency lighting all as to LEDS-C4 Manufacturer Model: ECOLED 90-1785-14-M3 or approved equivalent. | No. | 13 | #REF! | #REF! | #REF!
EL-23 | TOTAL TO COLLECTION PAGE |  |  |  | #REF!
FIRST FLOOR
WIRING ACCESSORIES
ALL SPECIFIED MATERIALS:
To be transported to site, connected up complete and commissioned in full working conditions including all necessary fixing/mounting accessories.
A | 10AX SP 1-Gang 1-Way white moulded plate switches c/w flush mounting box, as to LEGRAND Manufacture Model: Mallia Cat No. 281000, or approved equivalent. | No. | 43 | 8.875 | 381.625 | 31950
B | 10AX SP 3-Gang 1-Way white moulded plate switches c/w flush mounting box, as to LEGRAND Manufacture Model: Mallia Cat No. 281004, or approved equivalent. | No. | 1 | 12.2222 | 12.2222 | 44000
C | 10AX SP 1-Gang 2-Way white moulded plate switches c/w flush mounting box, as to LEGRAND Manufacture Model: Mallia Cat No. 281001, or approved equivalent. | No. | 2 | 8.875 | 17.75 | 31950
D | 13A SP 2-Gang white switched socket outlets c/w neon indicator and flush/trunking mounting box, as to to LEGRAND Manufacture Model: Belanko Cat No. 617047 or approved equivalent | No. | 73 | #REF! | #REF! | #REF!
E | 13A SP 2-Gang Non-Standard white switched socket outlets c/w neon indicator and flush mounting box, as to to LEGRAND Manufacture or approved equivalent | No. | 65 | 13.5 | 877.5 | 48600
F | 20AX DP Switch marked Water Heater/Hand dryer/AC with neon indicator and flush mounting box, as to LEGRAND Manufacture Model: Mallia Cat No. 281061 or approved equivalent | No. | 32 | #REF! | #REF! | #REF!
J | Three compartment box comprising 2No. Twin 13A Switched Socket Outlet + 1 Data Outlets + 1Voice Modules as to MK Manufacture or approved equivalent. | No. | 13 | 111.25 | 1446.25 | 400500
K | Multimedia Hub c/w 1No. 13A Multistandard (Universal) socket outlets, USB socket outlet, HDMI, RJ45 socket outlet, VGA all as to TELEADAPT Manufacture or equal and approved equivalent. | No. | 2 | 145 | 290 | 522000
L | RJ 45 category 6 Avaya twin socket module with 2MGS 400 connectors and 8 contacts without shutters c/w antique bronze flush mounting plate and accessory box as to LEGRAND or approved equivalent | No. | 65 | 13.5 | 877.5 | 48600
M | 2 Way Co-axial UHF, VHF sockect outlet complete with flush mounting box as Crabtree List No.7268, or approved equivalent. | No. | 8 | 13.5 | 108 | 48600
FIXED APPLIANCES:
N | 2.3kW/240V "No-Touch" hand drier, earthed Class 1 shock protection, motor type 2700 rpm brushless external rotor, low-noise fan with noise level of 65dBA @ 1 meter cut-outs, as to HEATRAE SADIA Product Code No.95:020:080, or approved equivalent. | No. | 2 | #REF! | #REF! | #REF!
EL-24 | TOTAL TO COLLECTION PAGE |  |  |  | #REF!
FIRST FLOOR
WIRING
Lighting points:
A | All Lighting points in office areas to be connected complete and ready from 10A/16A SP miniature circuit breakers of consumer unit, using 2.5mm² SC PVC-Insulated copper cables in radial circuits, drawn in uPVC flush conduits, through walls/switches/time switch, as per drawings. | No. | 170 | #REF! | #REF! | #REF!
B | All Lighting points for the warehouse to be connected complete and ready from 10A/16A SP miniature circuit breakers of consumer unit, using 2.5mm² SC PVC-Insulated copper cables in radial circuits, drawn in Galvanised Iron (GI) conduits, through walls/switches/time switch, as per drawings. | No. | 46 | #REF! | #REF! | #REF!
Raw Power points:
C | Power points to be connected complete and ready from 32A SP miniature circuit breakers of of the repective Distribution Boards , using 2.5mm² SC PVC-Insulated stranded copper cables in ring circuits, drawn in uPVC flush installed conduits,as per drawings. | No. | 87 | #REF! | #REF! | #REF!
UPS Power points:
D | Power points to be connected complete and ready from 32A SP miniature circuit breakers of of the repective Distribution Boards, using 2.5mm² SC PVC-Insulated stranded copper cables in ring circuits, drawn in uPVC flush installed conduits,as per drawings. | No. | 79 | #REF! | #REF! | #REF!
Muti-Media Hub Points:
E | All wiring of Multi-Media Hub points to be connected complete and ready using 2.5mm sq. SC PVC-Insulated stranded copper cables and co-axial cables or approved equivalent, drawn in uPVC flush installed conduits/trunking, as per drawings | No. | 2 | #REF! | #REF! | #REF!
Air Conditioning Points:
F | All wiring of air conditioning points are to be connected, complete and ready from 20A SP miniature circuit breaker of Distribution Board (DB-AC), using 2.5mm sq. SC PVC-Insulated stranded copper cables, drawn in uPVC flush installed conduits, as per drawings. | No. | 34 | #REF! | #REF! | #REF!
Television points:
G | All wiring of television points to be connected complete and ready using co-axial cables or approved equivalent, drawn in uPVC flush installed conduits, as per drawings | No. | 8 | #REF! | #REF! | #REF!
Hand Dryer Points:
H | All wiring of hand dryer points to be connected complete and ready from 16A SP miniature circuit breakers of Distribution Board (DB-1), in 2.5mm sq. SC PVC-Insulated stranded copper cables in radial circuits, drawn in uPVC flush installed conduits, , as per drawings | No. | 2 | #REF! | #REF! | #REF!
Extract Fan Points:
I | Extract Fan points to be connected complete and ready from 10A/16A SP miniature circuit breakers of the repective Distribution Boards, using 2.5mm² SC PVC-Insulated copper cables in radial circuits, drawn in uPVC flush conduits, through walls/switches/time switch, as per drawings. | No. | 4 | #REF! | #REF! | #REF!
Data/ Telephone points:
J | All wiring of telephone points to be connected complete and ready using 4-pair UTP cable of category 6 performance or better approved equivalent, drawn in Trunking, as per drawings | No. | 76 | #REF! | #REF! | #REF!
Earthing:
H | Earth the installation as per Regulations and Code of Practice, so as to achieve a final earth resistance value NOT exceeding 1.00 Ohm. | ITEM | 1 | #REF! | #REF! | #REF!
EL-25 | TOTAL TO COLLECTION PAGE |  |  |  | #REF!
COLLECTION PAGE FOR FIRST FLOOR
| FROM PAGE EL-19 |  |  |  | #REF!
| FROM PAGE EL-20 |  |  |  | 19817.875
| FROM PAGE EL-21 |  |  |  | #REF!
| FROM PAGE EL-22 |  |  |  | #REF!
| FROM PAGE EL-23 |  |  |  | #REF!
| FROM PAGE EL-24 |  |  |  | #REF!
| FROM PAGE EL-25 |  |  |  | #REF!
EL-26 | TOTAL TO SUMMARY PAGE |  |  |  | #REF!

## GH (hidden)
PROPOSED LABOREX MANUFACTURING, STORAGE AND DISTRIBUTION FACILITY ON PLOT 909, NAMANVE INDUSTRIAL PARK, MUKONO DISTRICT
ELECTRICAL INSTALLATION - BILLS OF QUANTITIES
Electrical Drawings Nos:
Item | Description and Specification | Unit | Qty | Rate (USD) | Amount (USD) | Rate (Ugx)
GATEHOUSE,POWER ROOM & SITE LIGHTING
LV POWER/RETICULATION/DISTRIBUTION SYSTEM
SUB-MAIN DISTRIBUTION BOARDS:
Note: Contractor to submit the manufacturer's specification and working drawings for the Engineer's approval before purchase
A | Metalcased with lockable hinged door 100A; 6-Way SPN MCB-TYPE Distribution Board (DB-G), c/w 1No.x 10A MCBs, 2No.x 20A MCBs and 3No. x SP Spare way blanking plates,all as to SCHENEIDER ELECTRIC manufacture or approved equivalent (Gate House) | No. | 1 | #REF! | #REF! | #REF!
B | Metalcased with lockable hinged door 100A; 4Way SPN MCB-TYPE Distribution Board (DB-PR), c/w 2No.x 10A MCBs, 1No.x 20A MCBs and1No. x SP Spare way blanking plates,all as to SCHENEIDER ELECTRIC manufacture or approved equivalent (Power Room) | No. | 1 | 137.5 | 137.5 | 495000
LV POWER/RETICULATION/DISTRIBUTION CABLES
NOTES:
i) | To be supplied and installed c/w all necessary fixing/clipping/supporting/termination accessories as per general specification
ii) | The rate shall cover excavation, sand-bedding,backfilling, trenching e.t.c, and all manholes, where necessary, and all associated builders' works
iii) | All cables are to be as per general specification and type-approved by the supervising Electrical Consultant
C | 600/1000V 10mm sq 3-Core XLPE-SWA-PVC-I copper cables connected from the Main Distribution Board (MDB) and terminated onto the 100A; Gate House Distribution Board (DB-G) as per drawings, c/w all necessary connecting accessories (Provisional Route Length). | L/m | 20 | #REF! | #REF! | #REF!
D | 600/1000V 10mm sq 3-Core XLPE-SWA-PVC-I copper cables connected from the Main Distribution Board (MDB) and terminated onto the 100A; Power Room Distribution Board (DB-P) as per drawings, c/w all necessary connecting accessories (Provisional Route Length). | L/m | 5 | #REF! | #REF! | #REF!
EL-27 | TOTAL TO COLLECTION PAGE |  |  |  | #REF!
LIGHTING FITTINGS
To be transported to site, connected up complete and commissioned in full working conditions including all necessary fixing/mounting accessories.
A | 1200mm 1x36W Single tube fluorescent basic batten fitting for T8 lamps c/w prismatic controller and lamp as to FITZGERALDDEP136/840 or approved equivalent. | No. | 1 | 63.75 | 63.75 | 229500
B | 600mm 1x18W Single tube fluorescent basic batten fitting for T8 lamps c/w prismatic controller and lamp as to FITZGERALD DEP118/840 or approved equivalent. | No. | 2 | 63.75 | 127.5 | 229500
C | IP65 stylish, robust, wall mounted vandal resistant luminaire with 1 x 40W LED lamp. Material in Vandal resistant diecast Alminium Body with UV stabilized polycarbonate diffuser and all gaskets manufactured from heat resistant silicone rubber to ensure IP65 rating. As to FITZGERALD LED PALADINE SQUARE PALS 40/CO/840 or approved equivalent. | No. | 7 | #REF! | #REF! | #REF!
D | 84W, highly efficient, general purpose, LED area floodlight. Electronic, LED control gear driving 36 LEDs at 700mA with asymmetrical distribution. IP66, IK08, Class I electrical. Body: recyclable, die-cast Aluminium (AS12U, EN AC-47100) powder coated dark grey. Enclosure: 5mm thick toughened glass. Integrated visor for precise lighting control. Reversable mounting stirrup supplied, optional spigot adaptors available separately for post top mounting. Complete with 4000K LED. As Thorn Areaflood LED AREA1 36L70 A/CB L740 CL1 or approved equivalent. | No. | 1 | 206.25 | 206.25 | 742500
E | 1200mm high performance IP65 dust and moisture resistant luminaire for aggressive atmospheres. For 2x36W T26 lamp(s) with electronic -fixed output circuit. Class I electrical. Canopy in light grey glass fibre reinforced polyester. Diffuser in acrylic with internal prisms. For surface or suspended mounting. For surface mounting c/w quick-fix installation brackets are supplied for surface mounting and 840 lamps as to THORN CORROSION FORCE II CORRF2 2x36W T26 HF L840 or approved equivalent. | No. | 2 | #REF! | #REF! | #REF!
F | 1xE-27 10W LED Outdoor base mount pillar luminaire with Polycarbonate body and lens. As Radiant L5859/BASKET or equal approved. (Boundary Wall). | No. | 11 | 107.5 | 1182.5 | 387000
G | LED Venture Bollard VEN36/CO/35/840 or approved equivalent | No. | 4 | 162.5 | 650 | 585000
EL-28 | TOTAL TO COLLECTION PAGE |  |  |  | #REF!
GATEHOUSE,POWER ROOM & SITE LIGHTING
WIRING ACCESSORIES
ALL SPECIFIED MATERIALS:
To be transported to site, connected up complete and commissioned in full working conditions including all necessary fixing/mounting accessories.
A | 10AX SP 1-Gang 1-Way white moulded plate switches c/w flush mounting box, as to LEGRAND Manufacture Model: Mallia Cat No. 281000, or approved equivalent. | No. | 4 | 8.875 | 35.5 | 31950
B | RJ 45 category 6 Avaya twin socket module with 2MGS 400 connectors and 8 contacts without shutters c/w antique bronze flush mounting plate and accessory box as to LEGRAND or approved equivalent | No. | 1 | 13.5 | 13.5 | 48600
C | 13A SP 2-Gang white switched socket outlets c/w neon indicator and flush/trunking mounting box, as to to LEGRAND Manufacture Model: Belanko Cat No. 617047 or approved equivalent | No. | 3 | 13.5 | 40.5 | 48600
D | 13A SP 1-Gang unswitched weather proof socket outlet c/w flush/trunking mounting box, as to to LEGRAND Manufacture Model: Plexo 66 Cat No. 684570 or approved equivalent | No. | 1 | 23.75 | 23.75 | 85500
E | 24-Hour programme time switch c/w fixing accessories and back-up battery (150 hours) and contactor, as to LEGRAND List No. 49951, or equivalent, including a suitable enclosure. | No. | 2 | #REF! | #REF! | #REF!
WIRING
Lighting points:
F | Interior Lighting points to be connected complete and ready from 10A/16A SP miniature circuit breakers of consumer unit, using 1.5mm² SC PVC-Insulated copper cables in radial circuits, drawn in uPVC flush conduits, through walls/switches/time switch, as per drawings. | No. | 7 | 35 | 245 | 126000
G | All wiring of External/ landscape /boundary wall lighting points to be connected complete and ready from 10A/16A SP miniature circuit breakers, using 2.5mm sq. 3-Core armoured copper cables, drawn in uPVC flush conduits, through wall/ grid switches, as per drawings. | No. | 11 | #REF! | #REF! | #REF!
Raw Power points:
H | Interior Power points to be connected complete and ready from 32A SP miniature circuit breakers of of the repective Distribution Boards , using 2.5mm² SC PVC-Insulated stranded copper cables in ring circuits, drawn in uPVC flush installed conduits,as per drawings. | No. | 3 | #REF! | #REF! | #REF!
I | Exterior Power points to be connected complete and ready from 20A SP miniature circuit breakers of of the repective Distribution Boards , using 2.5mm² 3-Core armoured copper cables in ring circuits, drawn in uPVC flush installed conduits,as per drawings. | No. | 1 | #REF! | #REF! | #REF!
Data/ Telephone points:
G | All wiring of telephone points to be connected complete and ready using 4-pair UTP cable of category 6 performance or better approved equivalent, drawn in Trunking, as per drawings | No. | 1 | #REF! | #REF! | #REF!
Earthing:
H | Earth the installation as per Regulations and Code of Practice, so as to achieve a final earth resistance value NOT exceeding 1.00 Ohm. | ITEM | 1 | #REF! | #REF! | #REF!
EL-29 | TOTAL TO COLLECTION PAGE |  |  |  | #REF!
COLLECTION PAGE FOR FIRST FLOOR
| FROM PAGE EL-27 |  |  |  | #REF!
| FROM PAGE EL-28 |  |  |  | #REF!
| FROM PAGE EL-29 |  |  |  | #REF!
EL-30 | TOTAL TO SUMMARY PAGE |  |  |  | #REF!

## STORAGE (hidden)
PROPOSED LABOREX MANUFACTURING, STORAGE AND DISTRIBUTION FACILITY ON PLOT 909, NAMANVE INDUSTRIAL PARK, MUKONO DISTRICT
ELECTRICAL INSTALLATION - BILLS OF QUANTITIES
Electrical Drawings Nos:
Item | Description and Specification | Unit | Qty | Rate (USD) | Amount (USD) | Rate (Ugx)
SALES REPRESENTATIVE STORAGE CONTAINERS
LV POWER/RETICULATION/DISTRIBUTION SYSTEM
SUB-MAIN DISTRIBUTION BOARDS:
Note: Contractor to submit the manufacturer's specification and working drawings for the Engineer's approval before purchase
A | Metalcased with lockable hinged door 100A; 8-Way SPN MCB-TYPE Distribution Board, c/w 2No. x 10A MCBs, 2No.x 32A MCBs, 2No. x 16A MCBs, 1No. x 40A MCBs and 1No.x SP Spare way blanking plates,all as to SCHENEIDER ELECTRIC manufacture or approved equivalent (DB-C1) | No. | 1 | 177.5 | 177.5 | 639000
B | Metalcased with lockable hinged door 63A; 8-Way SPN MCB-TYPE Distribution Board, c/w 2No. x 10A MCBs, 2No.x 32A MCBs, 1No. x 20A MCBs and 3No.x SP Spare way blanking plates,all as to SCHENEIDER ELECTRIC manufacture oR approved equivalent (DB-C2) | No. | 1 | 177.5 | 177.5 | 639000
LV POWER/RETICULATION/DISTRIBUTION CABLES
NOTES:
i) | To be supplied and installed c/w all necessary fixing/clipping/supporting/termination accessories as per general specification
ii) | The rate shall cover excavation, sand-bedding,backfilling, trenching e.t.c, and all manholes, where necessary, and all associated builders' works
iii) | All cables are to be as per general specification and type-approved by the supervising Electrical Consultant
C | 600/1000V 16mm sq 3-Core XLPE-SWA-PVC-I copper cables connected from the Main Distribution Board (MDB) and terminated onto the 100A; Consumer Unit (DB-C1) as per drawings, c/w all necessary connecting accessories (Provisional Route Length). | L/m | 100 | 13.125 | 1312.5 | 47250
D | 600/1000V 10mm sq 3-Core XLPE-SWA-PVC-I copper cables connected from the Consumer Unit (CU1) and terminated onto the 63A; Consumer Unit (CU2) as per drawings, c/w all necessary connecting accessories (Provisional Route Length). | L/m | 30 | 14.25 | 427.5 | 51300
EL-31 | TOTAL TO COLLECTION PAGE |  |  |  | 2095
LIGHTING FITTINGS
To be transported to site, connected up complete and commissioned in full working conditions including all necessary fixing/mounting accessories.
A | 1200mm 1x36W Surface mounted single tube high performance IP65 dust and moisture resistant flourescent luminaire in acrylic diffuser with internal prisms c/w T26 lamps, qucik-fix installation brackets as to THORN CORROSION FORCE II CORRF5 1X36W T26 HF L840/840 or approved equivalent. | No. | 14 | 63.75 | 892.5 | 229500
C | IP65 stylish, robust, wall mounted vandal resistant luminaire with 1 x 40W LED lamp. Material in Vandal resistant diecast Alminium Body with UV stabilized polycarbonate diffuser and all gaskets manufactured from heat resistant silicone rubber to ensure IP65 rating. As to FITZGERALD LED PALADINE SQUARE PALS 40/CO/840 or approved equivalent. | No. | 3 | #REF! | #REF! | #REF!
D | 84W, highly efficient, general purpose, LED area floodlight. Electronic, LED control gear driving 36 LEDs at 700mA with asymmetrical distribution. IP66, IK08, Class I electrical. Body: recyclable, die-cast Aluminium (AS12U, EN AC-47100) powder coated dark grey. Enclosure: 5mm thick toughened glass. Integrated visor for precise lighting control. Reversable mounting stirrup supplied, optional spigot adaptors available separately for post top mounting. Complete with 4000K LED. As Thorn Areaflood LED AREA1 36L70 A/CB L740 CL1 or approved equivalent. | No. | 2 | 206.25 | 412.5 | 742500
WIRING ACCESSORIES
ALL SPECIFIED MATERIALS:
To be transported to site, connected up complete and commissioned in full working conditions including all necessary fixing/mounting accessories.
0
E | 10AX SP 1-Gang 1-Way white moulded plate switches c/w flush mounting box, as to LEGRAND Cat No. 281000, or approved equivalent. | No. | 14 | 8.875 | 124.25 | 31950
0
F | 13A SP 2-Gang white switched socket outlets c/w neon indicator and flush/trunking mounting box, as to to LEGRAND Manufacture Model: Belanko Cat No. 617047 or approved equivalent | No. | 14 | #REF! | #REF! | #REF!
0
G | 24-Hour programme time switch c/w fixing accessories and back-up battery (150 hours) and contactor, as to LEGRAND List No. 49951, or equivalent, including a suitable enclosure. | No. | 1 | #REF! | #REF! | #REF!
WIRING
0
Lighting points:
H | Lighting points to be connected complete and ready from 10A/16A SP miniature circuit breakers of consumer unit, using 2.5mm² SC PVC-Insulated copper cables in radial circuits, drawn in uPVC flush conduits, through walls/switches/time switch, as per drawings. | No. | 19 | #REF! | #REF! | #REF!
0
Raw Power points:
I | Power points to be connected complete and ready from 32A SP miniature circuit breakers of of the repective Distribution Boards , using 2.5mm² SC PVC-Insulated stranded copper cables in ring circuits, drawn in uPVC flush installed conduits,as per drawings. | No. | 14 | #REF! | #REF! | #REF!
Earthing:
J | Earth the installation as per Regulations and Code of Practice, so as to achieve a final earth resistance value NOT exceeding 1.00 Ohm. | Item | 1 | 217.5 | 217.5 | 783000
EL-32 | TOTAL TO COLLECTION PAGE |  |  |  | #REF!
COLLECTION PAGE FOR FIRST FLOOR
| FROM PAGE EL-31 |  |  |  | 2095
| FROM PAGE EL-32 |  |  |  | #REF!
EL-33 | TOTAL TO SUMMARY PAGE |  |  |  | #REF!

## LIGHTNING PROTECTION
COMPLETION OF COFFEE ANALYTICAL LABORATORY &UCDA REGIONAL OFFICES AT RUKOKI KASESE.
ELECTRICAL INSTALLATION - BILLS OF QUANTITIES
Item | Description and Specification | Unit | Qty | Rate (UGX) | Amount (UGX) | Rate (Ugx)
LIGHTNING PROTECTION SYSTEM
All items are to be supplied and installed complete with all the required mounting/fixing/clipping/testing/connecting accesories; tested and commissioned to the satisfaction of the supervising Electrical Engineer, and handed over to the Employer in serviceable good working condition.
The works shall be executed as per Engineer's instructions on site, and as per conditions in the Specification and Codes of Practice:
A | 25 x 3mm PVC -Insulated copper tape as to FURSE Cat No. TC115, or approved equivalent. | L/m | 40 |  |  | 67500
B | 25 x 3mm PVC -Insulated copper square test clamp as to FURSE Cat No. CT 105, or approved equivalent. | No. | 2 |  |  | 63900
C | 2000mm x 15mm air rod as to FURSE Cat. No. RA 240 c/w multiple point usage, as to FURSE Cat. No. RA 600, or approved. | No. | 1 |  |  | 594000
D | Air terminals base, as to FURSE Cat. No. SD 105, or approved equivalent. | No. | 2 |  |  | 243000
E | Ridge saddle, as to FURSE Cat No. SD 115, or approved equivalent.(included) | No. | 1 |  |  | 198000
F | 1200mm x 20mm solid copper earth rods as to FURSE Cat No. RC 105, c/w driving studs and couplers, as necessary to achieve earth electrode resistance of not more than 10 ohms at all points. | No. | 2 |  |  | 169200
G | 25 x 3mm PVC -Insulated Copper tape clips, as to FURSE Cat No. CP517 | No. | 40 |  |  | 12960
H | Concrete inspection chamber, as to FURSE Cat No. PT005 | No. | 1 |  |  | 202500
I | Allow for inspection, testing and for improvement of earth electrode resistance values to comply with standards and the Specification attached hereto. | Item | 1 |  |  | 540000
EL-15 | TOTAL TO SUMMARY PAGE

## FIRE DETECTION
COMPLETION OF COFFEE ANALYTICAL LABORATORY &UCDA REGIONAL OFFICES AT RUKOKI KASESE.
ELECTRICAL INSTALLATION - BILLS OF QUANTITIES
Item | Description and Specification | Unit | Qty | Rate (UGX) | Amount (UGX) | Rate (Ugx)
FIRE DETECTION ALARM & DETECTION SYSTEM
GROUND FLOOR & FIRST FLOOR
Supply and install the following elements complete with all necessary mounting and fixing accessories of the HONEYWELL manufacture Analogue Addressable Fire Detection System or approved equivalent.
A | Single loop panel (no zone LEDs) English language control panel 230Vac, 2 sounder circuits. Supports the Morley-IAS protocol. Dimensions 260 x 390 x 147mm (H x W x D) c/w KIT DXc NETWORK CARD as to Honeywell Manufacture DXc1 714-001-112 or approved equivalent | Set. | 1 |  |  | 3240000
B | Morley Passive repeater. Includes enclosure with electronics carried on enclosure door, and user interface. | Set. | 1 |  |  | 1980000
C | Addressable Photo/optical detector c/w base B501AP-IV, without flange all as to Honeywell Manufacture MI-PSE-S2-IV , or approved equivalent. | No. | 38 |  |  | 445500
D | Addressable Thermal/heat detector c/w base B501AP-IV, without flange all as to Honeywell Manufacture , or approved equivalent. | No. | 1 |  |  | 445500
E | Addressable manual call point. Flexible element included. Requires SR1T for surface mounting or a single gang backbox for flush mounting. As to Honewell manufacture M5A-RP05FF-K013-01 or approved equivalent. | No. | 4 |  |  | 438300
F | Addressable AV PHASE II S/STROBE NON ISO c/w surface mount back-box skirt, wall mount, red all necessary accessories as to Honeywell Manufacture MI-WSS-PR-N , or approved equivalent. | No. | 3 |  |  | 576000
G | Loop wiring of Detection Elements using 1.5mm² 2-core Firetec OHLS 300/500V stranded copper cables to AEI CABLES LTD ref F2C1.5E or approved equivalent, drawn in u PVC flush installed conduits, as per drawings. (cable included) (conduit work). | No. | 39 |  |  | 143100
H | Allow for System programming, testing and commissioning | Item | 1 |  |  | 1800000
FD-1 | TOTAL FOR FIRE DETECTION AND ALARM SYSTEM TO MAIN COLLECTION PAGE

## CCTV
COMPLETION OF COFFEE ANALYTICAL LABORATORY &UCDA REGIONAL OFFICES AT RUKOKI KASESE.
ELECTRICAL INSTALLATION - BILLS OF QUANTITIES
Item | Description and Specification | Unit | Qty | Rate (UGX) | Amount (UGX) | Rate (Ugx)
A | 6 MP Bullet camera HD1080p,2MP CMOS Sensor, EXIR, 20m IR, Outdoor EXIR Bullet, ICR, 0.01 Lux/F1.2, 12 VDC, Smart IR, DNR, OSD Menu(Up the Coax), True WDR, IP66, 2.8/3.6/6mm Lens as to HIKVISION DS-2CE16D7T-IT1 or approved equivalent | No. | 8 |  |  | 1718910
B | 6MP Dome Camera HD1080p,2MP CMOS Sensor, EXIR, 20m IR, Outdoor EXIR Eyeball, ICR, 0.01 Lux/F1.2, 12 VDC, Smart IR, DNR, OSD Menu(Up the Coax), True WDR, IP66, 2.8/3.6/6mm Lens as to HIKVISION DS-2CE16D7T-IT1 or approved equivalent | No. | 12 |  |  | 1613475
C | 32 Channel NVR Turbo HD self-adaptive interfaces input, 32-ch video&4-ch audio input, 4 SATA interfaces, 1920×1080P: 12 fps/ch, 1280×720P:25(P)/30(N) fps/ch, alarm I/O: 16/4, 1.5U 19" case as to HIKVISION DS-7332HGHI-SH or approved equivalent | No. | 1 |  |  | 11342250
D | 6TB Video and Surveillance Hard Drive, 24x7 operation, low temperature, and best‐inclass reliability, for NVR/PVR and video surveillance applications as to WD40EURS or approved equivalent | No. | 1 |  |  | 360000
E | BNC Connector | No. | 36 |  |  | 24300
F | DC connector | No. | 24 |  |  | 24300
G | Coax Cable | No. | 26 |  |  | 24300
H | 4 core cable | Rolls | 3 |  |  | 318600
I | 18 Channel power supply | No. | 1 |  |  | 1386000
J | SCM-54 inch Industrial LCD/TFT Colour Monitor Ultra Sharp black 700:1 Contrast Ratio Maximum resolution 1280 x 1024.DVD/4Xusb 1216 ms Response time c/w mounting bracket | No | 1 |  |  | 4689000
K | Installation, Testing , Commissioing for CCTV | Item | 1 |  |  | 1800000
WIRING ACCESSORIES:
L | 13A SP 1-Gang white moulded plate switched socket outlets c/w neon indicator and white moulded plate surface mounting box, as to CRABTREE List No. 4304/3D, or approved equivalent, to be mounted at high level ( directly below the suspended ceiling grids), adjascent the location of each CCTV camera. | No. | 20 |  |  | 48600
WIRING CCTV POWER SUPPLY PROVISIONS:
M | All wiring of CCTV power supply points are to be connected in spur, complete and ready from the existing nearest ring circuitry wiring ( for small power socket outlets), using 2.5mm sq. SC PVC-Insulated stranded copper cables drawn in uPVC flush installed conduits/trunking as per CCTV layout drawings. | No. | 20 |  |  | 140400
WIRING CCTV SIGNAL CABLE ROUTE:
N | Allow for installation of flush installed uPVC conduits, ready for the signal cables to each CCTV camera point as per CCTV layout drawings. | lm | 620 |  |  | 24390
CCTV-1 | TOTAL TO COLLECTION PAGE |  |  |  | 0

## MAIN COLLECTION PAGE
COMPLETION OF COFFEE ANALYTICAL LABORATORY & REGIONAL OFFICES AT RUKOKI KASESE
MAIN COLLECTION PAGE
Item | Description & Specification | PAGE NO. | Amount (UGX)
1 | MAINS POWER SUPPLY | EL-3
2 | MAIN BLOCK | EL-14
3 | LIGHTNING PROTECTION | EL-15
4 | FIRE DETECTION AND ALARM SYSTEM | FD-1
5 | CCTV | CCTV-1
EL-S | TOTAL FOR ELECTRICAL INSTALLATIONS

## MAIN COLLECTION (hidden)
PROPOSED LABOREX MANUFACTURING, STORAGE AND DISTRIBUTION FACILITY ON PLOT 909, NAMANVE INDUSTRIAL PARK, MUKONO DISTRICT
MAIN COLLECTION PAGE
Electrical Drawings Nos:
Item | Description & Specification | PAGE NO. | Amount (USD)
1 | MAINS POWER SUPPLY | EL-4 | 0
2 | STANDBY POWER SUPPLY AND RETICULATION | EL-7 | #REF!
3 | GROUND FLOOR ELECTRICAL INSTALLATIONS | EL-18 | 0
4 | FIRST FLOOR ELECTRICAL INSTALLATIONS | EL-26 | #REF!
5 | GATE HOUSE, POWER HOUSE AND SITE LIGHTING | EL-29 | #REF!
6 | SALES REPRESENTATIVE STORAGE CONTAINERS | EL-32 | #REF!
7 | LIGHNING PROTECTION | EL-34 | 0
8 | VOICE AND DATA INSTALLATIONS | VD-1 | #REF!
9 | INTRUDER ALARM SYSTEM INSTALLATIONS | IA-1 | #REF!
10 | SECURITY SYSTEMS INSTALLATIONS | AC-S | #REF!
11 | FIRE DETECTION AND ALARM SYSTEM | FD-S | #REF!
12 | CCTV | CCTV-1 | #REF!
| SUB-TOTAL 1 |  | #REF!
| ADD CONTIGENCY (10%) | Included on Main Summary page | 0
| SUB-TOTAL 2 |  | #REF!
| ADD VAT (18%) |  | 0
EL-S | TOTAL |  | #REF!

## Summary (hidden)
SUMMARY PAGE
1899-12-31 | Section 1 - P & G | Page | -16- |  | #REF!
1900-01-02 | Section 2 - Builder's Works | Page | -58- |  | #REF!
1900-01-03 | Section 3- External works | Page | -88- |  | #REF!
| Total carried forward from Mechanical Installations bill |  |  | SUM | #REF!
| Total carried forward from Electrical Installations bill |  |  | SUM | #REF!
Sub total
|  |  |  | SUB Total 1 | #REF!
| Contingency |  |  | 5% | #REF!
| Sub total |  |  | SUB Total 2 | #REF!
| VAT | 18% |  |  | #REF!
| TOTAL AMOUNT INCLUDING VAT |  |  |  | #REF!
#REF!